## Sheet1
Task Name | Duration (Number of Days) | Starting Date
Deliverable 0 (Documentation) | 3 | 2016-01-10 | 10
Deliverable 1 (Documentation) | 15 | 2016-01-22 | 35
Deliverable 2 (Documentation) | 10 | 2016-02-22 | 25
Deliverable 3 (Documentation) | 15 | 2016-03-10 | 40
Basic Project Structure | 5 | 2016-01-10 | 6
Initial Diagrams | 5 | 2016-01-11 | 10
List of Features and Technologies Required | 10 | 2016-01-14 | 10
Proper Programming Environment | 2 | 2016-01-10 | 5
Implementation | 20 | 2016-01-14 | 75
Use Cases | 10 | 2016-01-26 | 15
User Interface | 10 | 2016-01-26 | 15
User Testing | 15 | 2016-02-28 | 55
Design of Script to Obtain Concordia Class Data | 1 | 2016-02-02 | 3
ER Diagram | 1 | 2016-02-06 | 3
Architecture Programming, Use Cases | 20 | 2016-02-19 | 60
Scope of Project | 60 | 2016-02-08 | 15
Test Cases | 12 | 2016-02-28 | 25
Performance | 8 | 2016-03-08 | 20
Design of UI / Aesthetics of Application | 10 | 2016-03-12 | 15
Debugging | 10 | 2016-03-22 | 45
Deliverable 4 : Final Report (Documentation) | 5 | 2016-04-06 | 25
| 247 |  | 512