## Sheet1
Task Name | # of days | Starting Date
Deliverable 0 | 3 | 2016-01-10
Deliverable 1 | 15 | 2016-01-22
Deliverable 2 | 15 | 2016-02-22
Deliverable 3 | 15 | 2016-03-10
Basic Project Structure Discussion | 5 | 2016-01-10
Initial Diagrams | 5 | 2016-01-11
List of Features and Technologies Required | 10 | 2016-01-14
Creation of Proper Programming Environment | 2 | 2016-01-10
Implementation Discussion | 10 | 2016-01-14
Use Cases | 10 | 2016-01-26
User Interface | 10 | 2016-01-26
User Testing | 20 | 2016-02-28
Design of Script to Obtain Concordia Class Data | 5 | 2016-02-02
ER Diagram Creation | 5 | 2016-02-06
Architecture Programming, Use Cases | 20 | 2016-02-19
Scope of Project | 60 | 2016-02-08
Test Cases | 12 | 2016-02-28
Performance | 8 | 2016-03-08
Design of UI / Aesthetics of Application | 10 | 2016-03-12
Debugging | 10 | 2016-03-22
250
42379